## Summary
Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary | Makoha P1.7 — 12-Month Budget and Funding Summary
Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified | Version 1.0 · 21 July 2026 · AUD ex GST · Scenario plan only · Opening cash, liabilities and founder capacity are unverified
Selected scenario | Base enterprise evidence
Opening cash |  | Gross 12-mo spend |  | Potential evidence revenue |  | Indicative financing requirement
0 |  | 1271200 |  | 50000 |  | 1475440
Average monthly spend |  | Peak monthly spend |  | Minimum reserve |  | Model status
105933.3333 |  | 117936 |  | 254240 |  | PROVISIONAL — VERIFY INPUTS
Scenario comparison | Scenario comparison | Scenario comparison | Scenario comparison | Scenario comparison | Scenario comparison | Scenario comparison | Scenario comparison
Scenario | Gross spend | Evidence revenue | Reserve | Indicative funding before cash | Safe 12-month outcome |  |  |  | Scenario | Indicative financing
Capital-constrained | 489500 | 30000 | 73425 | 532925 | Counsel, QMS foundation, synthetic assurance and partner discovery; no live clinical evidence assumption |  |  |  | Capital-constrained | 532925
Base enterprise evidence | 1271200 | 50000 | 254240 | 1475440 | Regulatory/QMS core, authority appointments, partner discovery and governed evidence readiness; live work only if gates pass |  |  |  | Base enterprise evidence | 1475440
Accelerated regulated build | 2403500 | 150000 | 600875 | 2854375 | Parallel product/QMS/authority build and larger evidence programme; still no automatic patient release |  |  |  | Accelerated regulated build | 2854375
Month | Closing cash before new funding
Aug 26 | -94360
Sept 26 | -193200
Oct 26 | -305424
Nov 26 | -416976
Dec 26 | -526960
Jan 27 | -643664
Feb 27 | -756600
Mar 27 | -863640
Apr 27 | -958960
May 27 | -1046552
June 27 | -1134456
July 27 | -1221200
Decision rule: use the Base enterprise evidence scenario for planning, but do not approve a raise amount or claim runway until opening cash, liabilities and founder capacity are verified. Live clinical evidence remains conditional on regulatory, authority, privacy, security and release gates. | Decision rule: use the Base enterprise evidence scenario for planning, but do not approve a raise amount or claim runway until opening cash, liabilities and founder capacity are verified. Live clinical evidence remains conditional on regulatory, authority, privacy, security and release gates. | Decision rule: use the Base enterprise evidence scenario for planning, but do not approve a raise amount or claim runway until opening cash, liabilities and founder capacity are verified. Live clinical evidence remains conditional on regulatory, authority, privacy, security and release gates. | Decision rule: use the Base enterprise evidence scenario for planning, but do not approve a raise amount or claim runway until opening cash, liabilities and founder capacity are verified. Live clinical evidence remains conditional on regulatory, authority, privacy, security and release gates. | Decision rule: use the Base enterprise evidence scenario for planning, but do not approve a raise amount or claim runway until opening cash, liabilities and founder capacity are verified. Live clinical evidence remains conditional on regulatory, authority, privacy, security and release gates. | Decision rule: use the Base enterprise evidence scenario for planning, but do not approve a raise amount or claim runway until opening cash, liabilities and founder capacity are verified. Live clinical evidence remains conditional on regulatory, authority, privacy, security and release gates. | Decision rule: use the Base enterprise evidence scenario for planning, but do not approve a raise amount or claim runway until opening cash, liabilities and founder capacity are verified. Live clinical evidence remains conditional on regulatory, authority, privacy, security and release gates. | Decision rule: use the Base enterprise evidence scenario for planning, but do not approve a raise amount or claim runway until opening cash, liabilities and founder capacity are verified. Live clinical evidence remains conditional on regulatory, authority, privacy, security and release gates.
Decision rule: use the Base enterprise evidence scenario for planning, but do not approve a raise amount or claim runway until opening cash, liabilities and founder capacity are verified. Live clinical evidence remains conditional on regulatory, authority, privacy, security and release gates. | Decision rule: use the Base enterprise evidence scenario for planning, but do not approve a raise amount or claim runway until opening cash, liabilities and founder capacity are verified. Live clinical evidence remains conditional on regulatory, authority, privacy, security and release gates. | Decision rule: use the Base enterprise evidence scenario for planning, but do not approve a raise amount or claim runway until opening cash, liabilities and founder capacity are verified. Live clinical evidence remains conditional on regulatory, authority, privacy, security and release gates. | Decision rule: use the Base enterprise evidence scenario for planning, but do not approve a raise amount or claim runway until opening cash, liabilities and founder capacity are verified. Live clinical evidence remains conditional on regulatory, authority, privacy, security and release gates. | Decision rule: use the Base enterprise evidence scenario for planning, but do not approve a raise amount or claim runway until opening cash, liabilities and founder capacity are verified. Live clinical evidence remains conditional on regulatory, authority, privacy, security and release gates. | Decision rule: use the Base enterprise evidence scenario for planning, but do not approve a raise amount or claim runway until opening cash, liabilities and founder capacity are verified. Live clinical evidence remains conditional on regulatory, authority, privacy, security and release gates. | Decision rule: use the Base enterprise evidence scenario for planning, but do not approve a raise amount or claim runway until opening cash, liabilities and founder capacity are verified. Live clinical evidence remains conditional on regulatory, authority, privacy, security and release gates. | Decision rule: use the Base enterprise evidence scenario for planning, but do not approve a raise amount or claim runway until opening cash, liabilities and founder capacity are verified. Live clinical evidence remains conditional on regulatory, authority, privacy, security and release gates.

## Assumptions
Makoha P1.7 — Planning Assumptions | Makoha P1.7 — Planning Assumptions | Makoha P1.7 — Planning Assumptions | Makoha P1.7 — Planning Assumptions | Makoha P1.7 — Planning Assumptions
Blue/yellow cells are editable assumptions. All monetary values are AUD, ex GST. Figures are planning hypotheses—not actuals, quotes or commitments. | Blue/yellow cells are editable assumptions. All monetary values are AUD, ex GST. Figures are planning hypotheses—not actuals, quotes or commitments. | Blue/yellow cells are editable assumptions. All monetary values are AUD, ex GST. Figures are planning hypotheses—not actuals, quotes or commitments. | Blue/yellow cells are editable assumptions. All monetary values are AUD, ex GST. Figures are planning hypotheses—not actuals, quotes or commitments. | Blue/yellow cells are editable assumptions. All monetary values are AUD, ex GST. Figures are planning hypotheses—not actuals, quotes or commitments.
Selected scenario index (1–3) | 2
Selected scenario | Base enterprise evidence
Verified opening cash | 0
Verified existing liabilities/commitments | 0
Founder available hours/week | 0
Opening cash verified? | NO
Liabilities verified? | NO
Founder capacity verified? | NO
Scenario annual costs and revenue assumptions | Scenario annual costs and revenue assumptions | Scenario annual costs and revenue assumptions | Scenario annual costs and revenue assumptions | Scenario annual costs and revenue assumptions
Category | Capital-constrained | Base enterprise evidence | Accelerated regulated build | Planning note
Founder / executive capacity | 60000 | 120000 | 150000 | Cash compensation and on-cost allowance; founder requirement unverified
Engineering, product and integrations | 120000 | 300000 | 550000 | Contractor/employee blend; no vendor quotes
Quality management and regulatory | 70000 | 180000 | 300000 | Class III-capable QMS and qualified regulatory support
Clinical authority, doctor and pharmacy input | 40000 | 150000 | 300000 | Appointments, protocol ownership and service-model design
Evidence, human factors and statistics | 30000 | 120000 | 300000 | Synthetic evidence first; live activity remains gated
Legal, privacy and corporate | 35000 | 70000 | 120000 | Contracts, data rights, privacy and corporate advice
Cloud, software, model and data services | 30000 | 60000 | 120000 | No live-health-data supplier commitments assumed
Cybersecurity and insurance | 25000 | 60000 | 100000 | Security testing and insurance allowances
Business development, travel and brand | 20000 | 45000 | 100000 | Founder-led enterprise sales; restrained external spend
Administration, accounting and tax | 15000 | 30000 | 50000 | Company administration and finance support
Subtotal before contingency | 445000 | 1135000 | 2090000 | Formula
Contingency % | 10% | 12% | 15% | Higher regulated execution intensity carries higher uncertainty
Contingency | 44500 | 136200 | 313500 | Formula
Gross 12-month spend | 489500 | 1271200 | 2403500 | Formula
Potential governed evidence revenue | 30000 | 50000 | 150000 | Assumption only; no production revenue included
Minimum cash reserve % | 15% | 20% | 25% | Planning reserve, not a solvency opinion
Minimum cash reserve | 73425 | 254240 | 600875 | Formula
Indicative funding need before opening cash/liabilities | 532925 | 1475440 | 2854375 | Gross spend less evidence revenue plus reserve
Planned financing schedule — editable; default is zero | Planned financing schedule — editable; default is zero | Planned financing schedule — editable; default is zero | Planned financing schedule — editable; default is zero | Planned financing schedule — editable; default is zero | Planned financing schedule — editable; default is zero | Planned financing schedule — editable; default is zero | Planned financing schedule — editable; default is zero | Planned financing schedule — editable; default is zero | Planned financing schedule — editable; default is zero | Planned financing schedule — editable; default is zero | Planned financing schedule — editable; default is zero | Planned financing schedule — editable; default is zero
| 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01
Financing inflow | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Phasing
Monthly Phasing Drivers | Monthly Phasing Drivers | Monthly Phasing Drivers | Monthly Phasing Drivers | Monthly Phasing Drivers | Monthly Phasing Drivers | Monthly Phasing Drivers | Monthly Phasing Drivers | Monthly Phasing Drivers | Monthly Phasing Drivers | Monthly Phasing Drivers | Monthly Phasing Drivers | Monthly Phasing Drivers | Monthly Phasing Drivers
Every annual cost and potential evidence-revenue assumption is phased across 12 months. Each row must total 100%. | Every annual cost and potential evidence-revenue assumption is phased across 12 months. Each row must total 100%. | Every annual cost and potential evidence-revenue assumption is phased across 12 months. Each row must total 100%. | Every annual cost and potential evidence-revenue assumption is phased across 12 months. Each row must total 100%. | Every annual cost and potential evidence-revenue assumption is phased across 12 months. Each row must total 100%. | Every annual cost and potential evidence-revenue assumption is phased across 12 months. Each row must total 100%. | Every annual cost and potential evidence-revenue assumption is phased across 12 months. Each row must total 100%. | Every annual cost and potential evidence-revenue assumption is phased across 12 months. Each row must total 100%. | Every annual cost and potential evidence-revenue assumption is phased across 12 months. Each row must total 100%. | Every annual cost and potential evidence-revenue assumption is phased across 12 months. Each row must total 100%. | Every annual cost and potential evidence-revenue assumption is phased across 12 months. Each row must total 100%. | Every annual cost and potential evidence-revenue assumption is phased across 12 months. Each row must total 100%. | Every annual cost and potential evidence-revenue assumption is phased across 12 months. Each row must total 100%. | Every annual cost and potential evidence-revenue assumption is phased across 12 months. Each row must total 100%.
Category | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | Total
Founder / executive capacity | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 100%
Engineering, product and integrations | 5% | 5% | 7% | 7% | 8% | 8% | 9% | 9% | 10% | 10% | 11% | 11% | 100%
Quality management and regulatory | 15% | 15% | 12% | 10% | 8% | 8% | 7% | 7% | 5% | 5% | 4% | 4% | 100%
Clinical authority, doctor and pharmacy input | 5% | 8% | 10% | 10% | 10% | 10% | 10% | 10% | 8% | 7% | 6% | 6% | 100%
Evidence, human factors and statistics | 0% | 0% | 5% | 10% | 10% | 15% | 15% | 15% | 15% | 10% | 5% | 0% | 100%
Legal, privacy and corporate | 20% | 15% | 10% | 10% | 8% | 8% | 7% | 5% | 5% | 5% | 4% | 3% | 100%
Cloud, software, model and data services | 5% | 5% | 6% | 6% | 7% | 7% | 8% | 9% | 10% | 11% | 12% | 14% | 100%
Cybersecurity and insurance | 5% | 10% | 15% | 10% | 10% | 10% | 10% | 10% | 5% | 5% | 5% | 5% | 100%
Business development, travel and brand | 5% | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 5% | 5% | 100%
Administration, accounting and tax | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 100%
Potential governed evidence revenue | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 20% | 30% | 30% | 10% | 0% | 100%

## Monthly Plan
Makoha 12-Month Cash Plan | Makoha 12-Month Cash Plan | Makoha 12-Month Cash Plan | Makoha 12-Month Cash Plan | Makoha 12-Month Cash Plan | Makoha 12-Month Cash Plan | Makoha 12-Month Cash Plan | Makoha 12-Month Cash Plan | Makoha 12-Month Cash Plan | Makoha 12-Month Cash Plan | Makoha 12-Month Cash Plan | Makoha 12-Month Cash Plan | Makoha 12-Month Cash Plan | Makoha 12-Month Cash Plan | Makoha 12-Month Cash Plan
Scenario-driven plan from August 2026 to July 2027. No production revenue, patient fees or uncontracted doctor-service revenue is assumed. | Scenario-driven plan from August 2026 to July 2027. No production revenue, patient fees or uncontracted doctor-service revenue is assumed. | Scenario-driven plan from August 2026 to July 2027. No production revenue, patient fees or uncontracted doctor-service revenue is assumed. | Scenario-driven plan from August 2026 to July 2027. No production revenue, patient fees or uncontracted doctor-service revenue is assumed. | Scenario-driven plan from August 2026 to July 2027. No production revenue, patient fees or uncontracted doctor-service revenue is assumed. | Scenario-driven plan from August 2026 to July 2027. No production revenue, patient fees or uncontracted doctor-service revenue is assumed. | Scenario-driven plan from August 2026 to July 2027. No production revenue, patient fees or uncontracted doctor-service revenue is assumed. | Scenario-driven plan from August 2026 to July 2027. No production revenue, patient fees or uncontracted doctor-service revenue is assumed. | Scenario-driven plan from August 2026 to July 2027. No production revenue, patient fees or uncontracted doctor-service revenue is assumed. | Scenario-driven plan from August 2026 to July 2027. No production revenue, patient fees or uncontracted doctor-service revenue is assumed. | Scenario-driven plan from August 2026 to July 2027. No production revenue, patient fees or uncontracted doctor-service revenue is assumed. | Scenario-driven plan from August 2026 to July 2027. No production revenue, patient fees or uncontracted doctor-service revenue is assumed. | Scenario-driven plan from August 2026 to July 2027. No production revenue, patient fees or uncontracted doctor-service revenue is assumed. | Scenario-driven plan from August 2026 to July 2027. No production revenue, patient fees or uncontracted doctor-service revenue is assumed. | Scenario-driven plan from August 2026 to July 2027. No production revenue, patient fees or uncontracted doctor-service revenue is assumed.
Metric | Aug 26 | Sept 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | June 27 | July 27 | 12-mo total | Budget/check
| 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01
Opening cash | 0 | -94360 | -193200 | -305424 | -416976 | -526960 | -643664 | -756600 | -863640 | -958960 | -1046552 | -1134456
Potential evidence revenue | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 10000 | 15000 | 15000 | 5000 | 0 | 50000
Planned financing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash available before costs | 0 | -94360 | -193200 | -305424 | -416976 | -526960 | -638664 | -746600 | -848640 | -943960 | -1041552 | -1134456
Operating expenditure | Operating expenditure | Operating expenditure | Operating expenditure | Operating expenditure | Operating expenditure | Operating expenditure | Operating expenditure | Operating expenditure | Operating expenditure | Operating expenditure | Operating expenditure | Operating expenditure | Operating expenditure | Operating expenditure
Founder / executive capacity | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 120000 | 120000
Engineering, product and integrations | 15000 | 15000 | 21000 | 21000 | 24000 | 24000 | 27000 | 27000 | 30000 | 30000 | 33000 | 33000 | 300000 | 300000
Quality management and regulatory | 27000 | 27000 | 21600 | 18000 | 14400 | 14400 | 12600 | 12600 | 9000 | 9000 | 7200 | 7200 | 180000 | 180000
Clinical authority, doctor and pharmacy input | 7500 | 12000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 12000 | 10500 | 9000 | 9000 | 150000 | 150000
Evidence, human factors and statistics | 0 | 0 | 6000 | 12000 | 12000 | 18000 | 18000 | 18000 | 18000 | 12000 | 6000 | 0 | 120000 | 120000
Legal, privacy and corporate | 14000 | 10500 | 7000 | 7000 | 5600 | 5600 | 4900 | 3500 | 3500 | 3500 | 2800 | 2100 | 70000 | 70000
Cloud, software, model and data services | 3000 | 3000 | 3600 | 3600 | 4200 | 4200 | 4800 | 5400 | 6000 | 6600 | 7200 | 8400 | 60000 | 60000
Cybersecurity and insurance | 3000 | 6000 | 9000 | 6000 | 6000 | 6000 | 6000 | 6000 | 3000 | 3000 | 3000 | 3000 | 60000 | 60000
Business development, travel and brand | 2250 | 2250 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 2250 | 2250 | 45000 | 45000
Administration, accounting and tax | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 30000 | 30000
Opening liabilities / commitments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal before contingency | 84250 | 88250 | 100200 | 99600 | 98200 | 104200 | 105300 | 104500 | 98500 | 91600 | 82950 | 77450 | 1135000 | 1135000
Contingency | 10110 | 10590 | 12024 | 11952 | 11784 | 12504 | 12636 | 12540 | 11820 | 10992 | 9954 | 9294 | 136200 | 136200
Gross cash spend | 94360 | 98840 | 112224 | 111552 | 109984 | 116704 | 117936 | 117040 | 110320 | 102592 | 92904 | 86744 | 1271200 | 1271200
Net cash flow | -94360 | -98840 | -112224 | -111552 | -109984 | -116704 | -112936 | -107040 | -95320 | -87592 | -87904 | -86744 | -1221200
Closing cash | -94360 | -193200 | -305424 | -416976 | -526960 | -643664 | -756600 | -863640 | -958960 | -1046552 | -1134456 | -1221200 | -1221200

## Milestones
12-Month Milestone and Gate Plan | 12-Month Milestone and Gate Plan | 12-Month Milestone and Gate Plan | 12-Month Milestone and Gate Plan | 12-Month Milestone and Gate Plan | 12-Month Milestone and Gate Plan | 12-Month Milestone and Gate Plan
Month | Workstream | Milestone | Required exit evidence | Accountable owner | Budget emphasis | Gate
Aug 2026 | Control baseline | Verify cash, liabilities, capacity and current build baseline | Signed finance inputs; fresh build/gap reconciliation | Founder / Finance / Engineering | Founder; finance; engineering | G0 — finance truth
Sep 2026 | Regulatory and authority | Freeze intended purposes; commission counsel; begin authority appointments | Counsel instruction accepted; role descriptions; candidate diligence | Founder / Regulatory / Board | QMS/regulatory; clinical | G1 — authority path
Oct 2026 | QMS and design controls | Approve QMS gap assessment and controlled design plan | QMS roadmap, design plan, risk-management framework and owners | Quality / Regulatory / Engineering | QMS/regulatory; engineering | G1
Nov 2026 | Design-partner discovery | Complete Pharmacy 777 synthetic discovery if authorised | Authority map, system/non-duplication map, user evidence and go/no-go | Founder / Growth / Clinical | BD; clinical; legal | G2 — partner fit
Dec 2026 | Evidence design | Freeze narrow evidence question and protocol | Approved endpoints, human factors, data and statistical plan | Clinical safety / Evidence / Quality | Evidence; clinical; legal | G3 — protocol
Jan 2027 | Product assurance | Close priority synthetic verification and integration gaps | Blocking test results, provenance and change-impact evidence | Engineering / Quality / Clinical safety | Engineering; cloud; cyber | G3
Feb 2027 | Commercial conversion | Negotiate separately priced evidence phase | Non-exclusive SOW, data schedule, costs and success criteria | Founder / Legal / Finance | Legal; BD; finance | G3
Mar 2027 | Evidence readiness | Independent readiness review | Authority appointments, protocol, privacy, security, regulatory and release gates current | Committee / Quality / Regulatory | Clinical; QMS; cyber | G4 — live evidence eligibility
Apr 2027 | Governed evidence | Run only the evidence activity authorised at G4 | Protocol adherence, incident controls and traceable results | Clinical investigator / Quality | Evidence; clinical; engineering | Conditional G4
May 2027 | Review and CAPA | Analyse evidence; close findings without overstating conclusions | Signed report, CAPA/change decisions and claims review | Evidence / Clinical safety / Quality | Evidence; QMS | G5 — evidence conclusion
Jun 2027 | Enterprise readiness | Test paid model, implementation economics and second-account pipeline | Buyer price evidence, COGS, deployment plan and non-exclusive pipeline | Founder / Finance / Growth | BD; finance; engineering | G5
Jul 2027 | Board/founder gate | Approve next 12-month plan and funding action | Runway, risk, regulatory, evidence and commercial gate pack | Founder / Board / Committee | All | G6 — continue/pivot/stop

## Checks
Model Checks and Limitations | Model Checks and Limitations | Model Checks and Limitations | Model Checks and Limitations | Model Checks and Limitations | Model Checks and Limitations | Model Checks and Limitations
Check | Actual | Expected | Difference | Tolerance | Status | Where to fix / note
Scenario selector valid | 2 | 2 | 0 | 1 | OK | Assumptions!B4
All phasing rows total 100% | 1 | 1 | 2.2204e-16 | 1e-06 | OK | Phasing!N4:N14
Monthly gross spend ties to selected annual budget | 1271200 | 1271200 | 0 | 1 | OK | Monthly Plan!N24
Monthly evidence revenue ties to selected annual assumption | 50000 | 50000 | 0 | 1 | OK | Monthly Plan!N6
Cash roll-forward arithmetic | -1221200 | -1221200 | 0 | 1 | OK | Monthly Plan!B5:M26
Opening cash verified | 0 | 1 | -1 | 0 | INPUT REQUIRED | Assumptions!B6/B9
Liabilities verified | 0 | 1 | -1 | 0 | INPUT REQUIRED | Assumptions!B7/B10
Founder capacity verified | 0 | 1 | -1 | 0 | INPUT REQUIRED | Assumptions!B8/B11
Structural checks failed | 0
Required inputs missing | 3
MODEL STATUS | PROVISIONAL — VERIFY INPUTS
Interpretation | PASS means formulas and required founder inputs are current; PROVISIONAL means structural checks pass but finance inputs are unverified.

## Sources
Sources and Audit Trail | Sources and Audit Trail | Sources and Audit Trail | Sources and Audit Trail | Sources and Audit Trail | Sources and Audit Trail | Sources and Audit Trail | Sources and Audit Trail | Sources and Audit Trail
Item | Value / use | Units | As-of | Source type | Source / location | Owner | Confidence | Notes
Finance truth | Cash, liabilities, burn and capacity | AUD / hours | 2026-07-21 | Required founder input | 03_ARTEFACTS/P1.7_FOUNDER_FINANCE_INPUT_SHEET.md | Founder | Missing | Zero placeholders in Assumptions are not actuals
Regulatory posture | Regulated SaMD base case; Class III-capable shared controls | Decision | 2026-07-20 | Controlled record | 02_PHASES/P1/P1.6_REGULATORY_PATH_DECISION.md | Founder / Regulatory | Provisional legal class | Counsel attestation open
Business model | Mixed enterprise, site/user, patient and service-agreement model | Decision | 2026-07-21 | Controlled record | 02_PHASES/P1/P1.3_BUSINESS_MODEL_AND_MOAT_THESIS.md | Founder / Finance | Unvalidated | No production revenue included in this workbook
Design partner | Six-week zero-fee synthetic-only Pharmacy 777 discovery | Offer | 2026-07-21 | Controlled record | 02_PHASES/P1/P1.5_DESIGN_PARTNER_OFFER.md | Founder / Growth | Issue authorised | Sender/counterparty gates remain
Authority model | Founder-led, independently governed authority stack | Decision | 2026-07-21 | Controlled record | 03_ARTEFACTS/P1.4_CLINICAL_AUTHORITY_BLUEPRINT.md | Founder / Board | Appointments missing | R-M019 open
Scenario costs | All annual cost values | AUD | 2026-07-21 | Internal planning assumption | This workbook: Assumptions!B15:D32 | Founder / Finance | Low | Not supplier quotes, payroll evidence or funding commitments
Evidence revenue | $30k / $50k / $150k by scenario | AUD | 2026-07-21 | Internal planning assumption | This workbook: Assumptions!B29:D29 | Founder / Growth | Low | Governed evidence projects only; no production/patient revenue